## Sheet1
Task | Start Date | Duration(Days) | Target date
Analysis
Read specification and think of idea | 2020-10-08 | 1 | 2020-10-09
Write outline of project | 2020-10-12 | 1 | 2020-10-13
Write scopes and boundaries | 2020-10-13 | 1 | 2020-10-14
Draw UML Case Diagram | 2020-10-14 | 1 | 2020-10-15
Write functional and end-user requirements | 2020-10-15 | 1 | 2020-10-16
Create a gantt chart | 2020-10-29 | 2 | 2020-11-02
Finish Project Plan | 2020-11-02 | 1 | 2020-11-03
Design
Create Wireframe of website | 2020-11-03 | 5 | 2020-11-10
Create pseudocode for program | 2020-11-10 | 7 | 2020-11-19
Create pseudocode for website | 2020-11-19 | 7 | 2020-11-30
Create Data Dictionary of array | 2020-11-30 | 3 | 2020-12-03
Implementation
Code basic website structure | 2020-12-03 | 3 | 2020-12-08
Code program | 2020-12-08 | 14 | 2021-01-08
Code rest of website | 2021-01-08 | 7 | 2021-01-19
Code website look and CSS | 2021-01-19 | 7 | 2021-01-28
Testing
Create test plan | 2021-01-28 | 3 | 2021-02-02
Test program | 2021-02-02 | 3 | 2021-02-05
Evaluate testing with problems faced | 2021-02-05 | 1 | 2021-02-08
Evaluation
Write Evaluation | 2021-02-08 | 2 | 2021-02-10
Holidays
2020-12-23 | 44112
2020-12-24 | 44224
2020-12-25 | 44237
2021-12-26
2020-12-27
2020-12-28
2020-12-29
2020-12-30
2021-01-01
2020-01-02
2021-01-03
2021-01-04
2021-01-05
Formulas:
Target date = WORKDAY([Start Date], [Duration(Days)])
Target date = WORKDAY([Start Date], [Duration(Days)], B32:B44)